## SUM
EMPLOYER: |  | AKAH
PROJECT: |  | AKAH Projects
FUNDS |  | Economic Cooperation and Development Division of the Swiss State Secretariat for Economic Affairs (SECO)
WORK PACKAGE: |  | KURP 20(b) "Pedestrian Bridge Construction in Khorog, Tajikistan"
|  |  | Дата/Date: | 10.01.2025
SUMMARY SHEET
BILL OF QUANTITIES
Construction of Pedestrian Bridge connecting Saifullo Abdullo to Barakat Mahalla, Khorog, Tajikistan
No | Work description |  |  | AMOUNT IN TJS
А | Construction of bridge foundation |  |  | 0
B | Bridge superstructure |  |  | 0
C | Outdoor electric lighting |  |  | 0
D | Preliminaries |  |  | 0
| TOTAL COST TJS (excluding VAT 7%) |  |  | 0
All the Figures are rounded up in the total column to two decimal places.
GENERAL NOTES:
* The Bill of Quantities shall be read in conjunction with the Technical Specification and the Tender Design. * Unit price shall include procurement, transportation, professional installing, inspection and all other related expenses, including services State Supervision Service for Architecture and Construction 0.15% * All works must be done professionally and according to this description, specifications, drawings, schemes and details * In case of any difference between BOQ, designs and/or drawings, the instruction of the supervisor Engineer will govern. * The contractor shall provide samples for all materials used in the project before delivery to get approval from the supervisor Engineer. * If the Contractor omits to price any items in the Bill of Quantities, the cost of work for such items will be considered included in the total amount.

## A
EMPLOYER: |  | AKAH
PROJECT: |  | AKAH Projects
FUNDS |  | Economic Cooperation and Development Division of the Swiss State Secretariat for Economic Affairs (SECO)
WORK PACKAGE: |  | KURP 20(b) "Pedestrian Bridge Construction in Khorog, Tajikistan"
|  |  |  | Date: | 10.01.2025
BILL OF QUANTITIES
Construction of Pedestrian Bridge connecting Saifullo Abdullo to Barakat Mahalla, Khorog, Tajikistan
No | Description | Unit | Quantity | Unit Price | Total Price
A | General builders works
1 | Preparatory and related work, temporary structures
1.1 | Preparatory work
1.1.1 | Mechanical planning of the construction site, soil group: 4 (t= 0.5m) | m2 | 600 |  | 0
1.2 | Construction and dismantling of temporary access roads to the foundation pits for supports
1.2.1 | Soil excovation when constructing a temporary access to the foundation pits for the dump using excavators 1.0 (1-1.2) m3, soil group: 4 | m3 | 2080 |  | 0
1.2.2 | Leveling of the upper surface of the excavation ramps using mechanical methods, soil group: 1. | m2 | 360 |  | 0
1.2.3 | Soil excovation with trailed rollers on pneumatic wheels 25 t per first pass along one track with layer thickness: 40 cm (6 passes) | m3 | 144 |  | 0
1.2.4 | Watering the compacted soil of embankments | m3 | 144 |  | 0
1.2.5 | Backfilling of ramps after completion of construction work with movement of up to 20 m using bulldozers with power: 96 (130) kW (hp), 4 group of soils | m3 | 2080 |  | 0
1.3 | Construction and dismantling of temporary dams
1.3.1 | Soil excovation during the construction of temporary dams with loading into dump trucks with excavators 1.0 (1-1.2) m3, soil group: 4 | m3 | 1150 |  | 0
1.3.2 | Transportation of soil over 15km | tn | 2300 |  | 0
1.3.3 | Repair and maintenance of unpaved earth-carrying roads 1 km long, soil group: 4 | m3 | 1150 |  | 0
1.3.4 | Soil compaction with trailed rollers on pneumatic wheels 25 t per first pass along one track with layer thickness: 50 cm (4 passes) | m3 | 1150 |  | 0
1.3.5 | Watering the compacted soil of embankments | m3 | 1150 |  | 0
1.3.6 | Protection of the slopes of temporary embankments (slope reinforcement of embankments) with large-sized stone up to 1 meter in size. | m3 | 210 |  | 0
1.3.2 | Transportation of stone up to 15 km | tn | 525 |  | 0
1.3.7 | Excovation of soil with movement up to 20 m by bulldozers with power: 96 (130) kW (hp), 4 group of soils | m3 | 862.5 |  | 0
Construction dismantling
1.3.8 | Loading and removal of construction waste for 10 km | tn | 2 |  | 0
| Итого / Total |  |  |  | 0
2 | Construction of foundations
2.1 | Construction of coastal support pillars
2.1 | Soil excovation when constructing pits for supports with loading into dump trucks with excavators 1.0 (1-1.2) m3, soil group: 4 | m3 | 680 |  | 0
2.2 | Soil development when backfilling a pit with loading into dump trucks with excavators 1.0 (1-1.2) m3, soil group: 4 | m3 | 281 |  | 0
2.3 | Transportation of soil over 10 km | tn | 1922 |  | 0
2.4 | Repair and maintenance of unpaved earth-carrying roads 1 km long, soil group: 4 | m3 | 96.1 |  | 0
2.5 | Manual completion of soil soil group: 4 | m3 | 66.8 |  | 0
2.6 | Leveling the bottom of the support pit using a mechanized method, soil group: 2 | m2 | 192 |  | 0
2.7 | Backfilling of foundation pits around the support foundations with large-sized stones." | m3 | 285 |  | 0
2.8 | Transportation of stone up to 15 km | tn | 712.5 |  | 0
2.9 | Moving up to 30m of soil of group 4 by a bulldozer during backfilling of support pits with layer-by-layer leveling up to 40 cm thick | m3 | 281 |  | 0
2.10 | Soil excovation with trailed rollers on pneumatic wheels 25 t per first pass along one track with layer thickness: 40 | m3 | 210.8 |  | 0
2.11 | Watering the compacted soil of embankments | m3 | 210.8 |  | 0
2.12 | Soil compaction with pneumatic tampers, soil group: 3, 4 | m3 | 70.25 |  | 0
2.13 | Construction of a gravel base | m3 | 19.2 |  | 0
2.14 | Lean monolithic concrete B10, grades F100 and W 4 | m3 | 7.038 |  | 0
2.15 | Pile drilling using impact-rope and rotary methods with casing pipes of 1200 mm diameter, using equipment for constructing bored piles in unstable soils of group 6 by drillability | m | 84 |  | 0
2.16 | Concrete B25, grades F200 and W 6 monolithic underwater for filling wells 97.22 m3 (pebble 6 g table 1.4 concrete consumption 1.32) using steel casing pipes D1200 mm | /m3 | 128.3304 |  | 0
2.17 | Reinforced mesh A-I d-8-10 mm (Russia) | tn | 1.1734 |  | 0
2.18 | Reinforced mesh A-I d-16 mm (Russia) | tn | 0.5451 |  | 0
2.19 | Reinforced mesh A-I d-22-25mm (Russia) | tn | 0.3052 |  | 0
2.20 | Reinforced mesh A-III d-22mm (Russia) | tn | 6.9924 |  | 0
2.21 | Knitting wire | tn | 0.0455 |  | 0
2.22 | Removing low-quality concrete from the top of piles | m3 | 2.26 |  | 0
2.23 | Construction of grillages from monolithic reinforced concrete B25, grades F200 and W4 | m3 | 69.12 |  | 0
2.24 | Reinforced mesh A-I d-8-10 mm (Russian) | tn | 0.081 |  | 0
2.25 | Reinforced mesh A-III d-10 mm (Russian) | tn | 0.104 |  | 0
2.26 | Reinforced mesh A-III d-12-16 mm (Russian) | tn | 2.572 |  | 0
2.27 | Reinforced mesh A-III d-22 mm (Russia) | tn | 2.197 |  | 0
2.28 | Knitting wire | tn | 0.025 |  | 0
2.29 | Construction of support bodies made of monolithic reinforced concrete B25, grades F200 and W6 | m3 | 111.84 |  | 0
2.30 | Reinforced mesh A-I d-16 mm (Russian) | tn | 0.428 |  | 0
2.31 | Reinforced mesh A-III d-10 mm (Russian) | tn | 0.07975 |  | 0
2.32 | Rebar A-III D-12-18 mm (Russian) | tn | 1.514 |  | 0
2.33 | Knitting wire | tn | 0.01 |  | 0
2.34 | Anchor made of round steel | tn | 0.07975 |  | 0
2.35 | Installation of anti-seismic supports made of monolithic reinforced concrete B25, grades F200 and W 4 | m3 | 3.21 |  | 0
2.36 | Reinforced mesh A-III d-10 mm (Russian) | tn | 0.175 |  | 0
2.37 | Rebar A-III D-12-18 mm (Russian) | tn | 0.054 |  | 0
2.38 | Knitting wire | tn | 0.001 |  | 0
2.39 | Construction of panel walls made of monolithic reinforced concrete B25, with grades F200 and W4 | m3 | 5.1 |  | 0
2.40 | Reinforced mesh A-I d-8-10 mm (Russian) | tn | 0.00588 |  | 0
2.41 | Reinforced mesh A-I d-12 mm (Russian) | tn | 0.044 |  | 0
2.42 | Rebar A-III D-12-18 mm (Russian | tn | 0.706 |  | 0
2.43 | Knitting wire | tn | 0.00379 |  | 0
2.44 | Installation of embedded parts | tn | 0.151 |  | 0
2.45 | Construction of support pillars made of monolithic reinforced concrete B25, with grades F200 and W4 | m3 | 0.22 |  | 0
2.46 | Reinforced mesh A-III d-10 mm (Russian) | tn | 0.0325 |  | 0
2.47 | Rebar A-III D-12-18 mm (Russian) | tn | 0.0171 |  | 0
2.48 | Knitting wire | tn | 0.0002 |  | 0
2.49 | Installation of embedded parts | tn | 0.071 |  | 0
2.50 | Coating bitumen waterproofing in 2 layers | m2 | 232 |  | 0
| Итого / Total |  |  |  | 0
A | RECAPITULATION
1 | Preparatory and related work, temporary structures |  |  |  | 0
2 | Construction of foundations |  |  |  | 0
A | GRAND TOTAL |  |  |  | 0
All the Figures are rounded up in the total column to two decimal places.
GENERAL NOTES:
* The Bill of Quantities shall be read in conjunction with the Technical Specification and the Tender Design. * Unit price shall include procurement, transportation, professional installing, inspection and all other related expenses, including services State Supervision Service for Architecture and Construction 0.15% * All works must be done professionally and according to this description, specifications, drawings, schemes and details * In case of any difference between BOQ, designs and/or drawings, the instruction of the supervisor Engineer will govern. * The contractor shall provide samples for all materials used in the project before delivery to get approval from the supervisor Engineer. * If the Contractor omits to price any items in the Bill of Quantities, the cost of work for such items will be considered included in the total amount.

## B
EMPLOYER: |  | AKAH
PROJECT: |  | AKAH Projects
FUNDS |  | Economic Cooperation and Development Division of the Swiss State Secretariat for Economic Affairs (SECO)
WORK PACKAGE |  | KURP 20(b) "Pedestrian Bridge Construction in Khorog, Tajikistan"
|  |  |  | Дата/Date: | 10.01.2025
BILL OF QUANTITIES
Construction of Pedestrian Bridge connecting Saifullo Abdullo to Barakat Mahalla, Khorog, Tajikistan"
No | Description | Unit | Quantity | Unit Price | Total Price
B | Bridge superstructure
1 | Construction of platforms and temporary supports for the assembly of bridge span structures
1.1 | Excovation during the construction of sites for the installation of superstructures with loading into dump trucks with excavators 1.0 (1-1.2) m3, soil group: 4 | m3 | 1200 |  | 0
1.2 | Transportation of soil up to 15 km | tn | 2400 |  | 0
1.3 | Soil compaction with trailed rollers on pneumatic wheels 25 t per first pass along one track with layer thickness: 50 cm (4 passes) | /m3 | 1200 |  | 0
1.4 | Watering the compacted soil of embankments | m3 | 1200 |  | 0
1.5 | Protection of the slopes of temporary embankments (slope reinforcement of embankments) with large-sized stones up to 1 meter in size (including transportation)." | m3 | 300 |  | 0
1.6 | Transportation of soil up to 15 km | tn | 750 |  | 0
1.7 | Excovation during dismantling of temporary sites with loading into dump trucks with excavators 1.0 (1-1.2) m3, soil group: 4 | m3 | 1800 |  | 0
1.8 | Transportation of soil to 10 km | tn | 3600 |  | 0
1.9 | Repair and maintenance of unpaved earth-carrying roads 1 km long, soil group: 4 | m3 | 1800 |  | 0
1.10 | Excovation of soil with movement of up to 10 m using bulldozers with power: 96 (130) kW (hp), 4 group of soils | m3 | 1800 |  | 0
1.11 | Excovation of soil with leveling in the river bed after dismantling construction sites for the installation of arches of the superstructure with movement of up to 30 m by bulldozers with power: 96 (130) kW (hp), 4 group of soils | m3 | 300 |  | 0
1.12 | Construction of foundations for temporary supports made of monolithic reinforced concrete B15 | m3 | 3.6 |  | 0
1.13 | Армосетка А-I д-8-10 мм Росийская | tn | 0.3 |  | 0
1.14 | Manufacturing and installation of temporary metal supports | tn | 5.6 |  | 0
1.15 | Dismantling temporary metal supports | tn | 5.6 |  | 0
| Total |  |  |  | 0
2 | Construction of the span
2.1 | Bridge superstructure made of steel arches with a span 1x75m
2.1.1 | Manufacturing and delivery of metal support parts from cast steel grade St 30L (GOST 977-88) | tn | 2.0196 |  | 0
2.1.2 | Installation of metal support parts made of cast steel grade St 30L (GOST 977-88) | tn | 2.0196 |  | 0
2.1.3 | Manufacturing and delivery of steel arches for the superstructure of a building (Steel structures GOST 6713-2021) | tn | 65.54 |  | 0
2.1.4 | Installation of steel arches of the superstructure (Steel structures GOST 6713-2021) | tn | 65.54 |  | 0
2.1.5 | High-strength bolts with nuts and washers: Bolts GOST 52644-2006, Nuts GOST 52645-2006, Washers GOST 52646-2006 | tn | 1.81 |  | 0
2.1.6 | Lifting of bridge superstructures to a height of up to 1 meter | m | 1 |  | 0
2.1.7 | Lowering spans to a height of 1m | m | 1 |  | 0
2.1.8 | Construction of supports from sleeper cages | sleepers | 32 |  | 0
2.1.9 | Dismantling supports from sleeper cages | sleepers | 32 |  | 0
2.1.10 | Manufacturing and installation of metal suspensions (28 sets) | tn | 4.25 |  | 0
2.1.11 | Manufacturing and installation of metal assembly trolleys during installation of arch sections, suspensions and painting of the span structure (4 sets) | tn | 0.4 |  | 0
2.1.12 | Removing metal mounting trolleys | tn | 0.4 |  | 0
2.1.13 | Arrangement of carts and scaffolding from timber | m3 | 4 |  | 0
2.1.14 | Dismantling the arrangement of carts and scaffolding made of timber | m3 | 4 |  | 0
2.1.15 | Manufacturing and installation of metal anti-seismic stops | tn | 0.1683 |  | 0
2.1.16 | One-time priming of metal surfaces with ED-20 primer | m2 | 1790 |  | 0
2.1.17 | Painting of metal structures 2 times with zinc white with the addition of aluminum powder 5-7% | m2 | 1790 |  | 0
2.2 | Pedestrian part of the bridge
2.2.1 | Manufacturing and delivery of metal beams for the pedestrian part from steel structure GOST 6713-2021 | tn | 15.6554 |  | 0
2.2.2 | Installation of metal beams of the pedestrian part from the steel structure GOST 6713-2021 | tn | 15.6554 |  | 0
2.2.3 | High-strength bolts with nuts and washers: Bolts GOST 52644-2006, Nuts GOST 52645-2006, Washers GOST 52646-2006. | tn | 0.48 |  | 0
2.2.4 | Installation of rubber-metal supporting parts 25x40x7.8 1 piece = 21 kg | pcs | 4 |  | 0
2.2.5 | Epoxy primer ED-20 | kg | 4 |  | 0
2.2.6 | Primer of metal structures of the span at one time using primer ED-20 | m2 | 483 |  | 0
2.2.7 | Painting the metal structures of the span in two layers with zinc white with the addition of aluminum powder 5-7% | m2 | 483 |  | 0
2.2.8 | Construction of scaffolding for painting with portable cradles (including disassembly) | m2 | 483 |  | 0
2.2.9 | Construction of a bridge roadway slab made of monolithic reinforced concrete B35, grades F200 and W6 with (formwork panels ЩД 1.2х0.4, size 1200х400х172 mm) | m3 | 34.63 |  | 0
2.2.10 | Reinforced mesh A-III d-10 mm Russian | tn | 2.46 |  | 0
2.2.11 | Reinforced mesh A-III d-12-16 mm Russian | tn | 4.28 |  | 0
2.2.12 | Проволока вязальная | tn | 0.034 |  | 0
2.2.13 | Installation of embedded parts | tn | 1.73 |  | 0
2.2.14 | Manual removal of poor-quality concrete from the top | m3 | 1.15 |  | 0
2.2.15 | Device of waterproofing TECHNOELASTMOST of the roadway on bridges without the device of a protective layer | m2 | 246.4 |  | 0
2.2.16 | Drainage devices made of pipes D=89x6 mm | m | 145 |  | 0
2.2.17 | Polymer bitumen mastic | kg | 30 |  | 0
2.2.18 | Laying device in 2 layers of roofing felt | m2 | 15 |  | 0
2.2.19 | Construction of a bridge walkway covering made of monolithic reinforced concrete B35, grades F200 and W6 (Formwork panels ЩД 1.2х0.4, size 1200х400х172 mm) | m3 | 11.96 |  | 0
2.2.20 | VR1-D-5mm mesh | tn | 0.753 |  | 0
2.2.21 | Installation of temperature joints t=1 cm with a step of 5.5 m, filling the joint with thiokol mastic | m | 39 |  | 0
2.2.22 | Installation of expansion joints of the MAURER system, type D 100, hot-dip galvanized or equivalent, with anti-corrosion protection (outer bearing profile - 2.0 (2.0) m per 1 running meter; strip profile - 1.0 m per 1 running meter) | m | 6 |  | 0
2.2.23 | Bearing profile | tn | 0.0648 |  | 0
2.2.24 | Bitumen mastic | kg | 42.3 |  | 0
2.2.25 | Rubber compensator | kg | 10.5 |  | 0
2.2.26 | Manufacture and delivery of metal railings on bridge spans (St3sp according to GOST 380-2005) | tn | 4.66 |  | 0
2.2.27 | Installation of metal railings on bridge spans with two-layer painting using zinc white with the addition of 5-7% aluminum powder | tn | 4.66 |  | 0
| Total |  |  |  | 0
3 | Structures of the ramps of the bridge
Construction of retaining walls
3.1 | Development of soil into a dump by excavators 1.0 (1-1.2) m3, soil group: 4 | m3 | 327.3 |  | 0
3.2 | Manual completion of soil soil group: 4 | m3 | 16.37 |  | 0
3.3 | Leveling the bottom of the excavation pit using a mechanized method, soil group: 4 | m2 | 334.9 |  | 0
3.4 | Manual backfilling of support pits soil group: 4 | m3 | 21.6 |  | 0
3.5 | Soil compaction with pneumatic tampers, soil group: 3, 4 | m3 | 5.4 |  | 0
3.6 | Construction of retaining walls made of masonry with cement mortar | m3 | 629.7 |  | 0
3.7 | Laying of large-sized stones with a size of 0.6m | m3 | 114.5 |  | 0
3.8 | Transportation of stones over a distance of 15 km | tn | 286.25 |  | 0
3.9 | Side coated bitumen waterproofing in 2 layers of backfilled surfaces | m3 | 66.2 |  | 0
3.10 | Installation of side curbs on retaining walls and edges of paving slabs concrete B25, grades F200 and W6 | m3 | 2.8 |  | 0
3.11 | Installation of embedded parts | tn | 0.04 |  | 0
| Total |  |  |  | 0
4 | Installation of staircases and ramps
4.1 | Installation of reinforced concrete stairways, curbs and slabs, concrete B25, grades F200 and W6 | m3 | 10.86 |  | 0
4.2 | Reinforced mesh A-I d-8-10 mm with extra charge | tn | 1.1166 |  | 0
4.3 | Reinforced mesh A-III d-10 mm Russian | tn | 0.119 |  | 0
4.4 | Knitting wire | tn | 0.0062 |  | 0
4.5 | Installation of embedded parts | tn | 0.11 |  | 0
4.6 | Construction of reinforced concrete ramps, curbs, and slabs of concrete grade B25, with marks F200 and W6 | m3 | 19.79 |  | 0
4.7 | Reinforced mesh A-I d-8-10 mm with extra charge | tn | 0.229 |  | 0
4.8 | Rebar A-III D-12-16 mm Russian | tn | 1.568 |  | 0
4.9 | Knitting wire | tn | 0.00933 |  | 0
4.10 | Installation of embedded parts | tn | 0.31 |  | 0
4.11 | Manufacture and delivery of metal railings with two-layer painting with zinc white with the addition of 5-7% aluminum powder (St3sp according to GOST 380-2005) | tn | 3.199 |  | 0
4.12 | Installation of metal railings with two-layer painting with zinc white with the addition of 5-7% aluminum powder ( according to GOST 380-2005) | tn | 3.199 |  | 0
| Total |  |  |  | 0
5 | Coating of sidewalk areas to the bridge ramps
5.1 | Installation of concrete paving stones on a cement-sand mixture of thickness. 3 cm. | m2 | 98.1 |  | 0
| Total |  |  |  | 0
B | RECAPITULATION
1 | Construction of platforms and temporary supports for the assembly of bridge span structures |  |  |  | 0
2 | Construction of the span |  |  |  | 0
3 | Structures of the ramps of the bridge |  |  |  | 0
4 | Installation of staircases and ramps |  |  |  | 0
5 | Coating of sidewalk areas to the bridge ramps |  |  |  | 0
B | GRAND TOTAL |  |  |  | 0
All the Figures are rounded up in the total column to two decimal places.
GENERAL NOTES:
* The Bill of Quantities shall be read in conjunction with the Technical Specification and the Tender Design. * Unit price shall include procurement, transportation, professional installing, inspection and all other related expenses, including services State Supervision Service for Architecture and Construction 0.15% * All works must be done professionally and according to this description, specifications, drawings, schemes and details * In case of any difference between BOQ, designs and/or drawings, the instruction of the supervisor Engineer will govern. * The contractor shall provide samples for all materials used in the project before delivery to get approval from the supervisor Engineer. * If the Contractor omits to price any items in the Bill of Quantities, the cost of work for such items will be considered included in the total amount.

## C
EMPLOYER: |  | AKAH / АКАX
PROJECT: |  | AKAH Projects / Проекты АКАX
FUND: |  | Economic Cooperation and Development Division of the Swiss State Secretariat for Economic Affairs (SECO)
WORK PACKAGE: |  | KURP 20(b) "Pedestrian Bridge Construction in Khorog, Tajikistan"
|  |  |  | Дата/Date: | 10.01.2025
BILL OF QUANTITIES
Construction of Pedestrian Bridge connecting Saifullo Abdullo to Barakat Mahalla, Khorog, Tajikistan"
No | Description | Unit | Quantity | Unit Price | Total Price
C | Outdoor electric lighting
1 | Outdoor electric lighting
1.1 | Installation of a crushed stone surface for the lighting control panel | m3 | 0.14 |  | 0
1.2 | Construction of a monolithic foundation for the lighting control panel, grade B15 | m3 | 0.21 |  | 0
1.3 | Manual soil development in soil trenches: 4 | m3 | 40.5 |  | 0
1.4 | Priming of metal surfaces of supports with primer GF-021 | m2 | 70 |  | 0
1.5 | Painting of supports with PF-115 enamel | m2 | 70 |  | 0
| Total |  |  |  | 0
2 | Installation work on external lighting
2.1 | Installation of a lamp (Floor lamp) h - 3m | pcs | 20 |  | 0
2.2 | Lighting control panel | pcs | 1 |  | 0
2.3 | Laying cable in trench AVBBShv section 4x50mm2 | m | 150 |  | 0
2.4 | Laying cable AVBBShv section 3x16+1x10 mm2 in PVC pipe | m | 150 |  | 0
2.5 | Laying a cable with copper conductors, non-flammable VVGng with a cross-section of 3x1.5mm2 | m | 100 |  | 0
2.6 | Round steel grounding rod with diameter 12mm | m | 7.6 |  | 0
2.7 | Vertical grounding rod made of round steel, diameter 16mm -1.5m | pcs | 6 |  | 0
2.8 | Grounding conductor made of channel 14L | m | 2.8 |  | 0
2.9 | Grounding rod made of round steel with a diameter of 6 mm | m | 6.2 |  | 0
2.10 | Grounding rod made of angle steel, size 50x50x4mm -2.5m | pcs | 1 |  | 0
2.11 | Vertical grounding rod made of angle steel, size 70x70x5mm -0.7m | pcs | 4 |  | 0
2.12 | Grounding conductor made of steel strip with a cross section of 40x4 mm | m | 2 |  | 0
2.13 | Polyethylene pipe diameter 80mm | m | 150 |  | 0
2.14 | Cable lug for 50mm cable | pcs | 8 |  | 0
2.15 | Cable lug for 16mm cable | pcs | 100 |  | 0
2.16 | Installation of photo a relay | pcs | 1 |  | 0
| Total |  |  |  | 0
C | RECAPITULATION
1 | Outdoor electric lighting |  |  |  | 0
2 | Installation work on external lighting |  |  |  | 0
C | GRAND TOTAL |  |  |  | 0
All the Figures are rounded up in the total column to two decimal places.
GENERAL NOTES:
* The Bill of Quantities shall be read in conjunction with the Technical Specification and the Tender Design. * Unit price shall include procurement, transportation, professional installing, inspection and all other related expenses, including services State Supervision Service for Architecture and Construction 0.15% * All works must be done professionally and according to this description, specifications, drawings, schemes and details * In case of any difference between BOQ, designs and/or drawings, the instruction of the supervisor Engineer will govern. * The contractor shall provide samples for all materials used in the project before delivery to get approval from the supervisor Engineer. * If the Contractor omits to price any items in the Bill of Quantities, the cost of work for such items will be considered included in the total amount.

## D
EMPLOYER: |  | AKAH
PROJECT: |  | AKAH Projects
FUND |  | Economic Cooperation and Development Division of the Swiss State Secretariat for Economic Affairs (SECO)
WORK PACKAGE: |  | KURP 20(b) "Pedestrian Bridge Construction in Khorog, Tajikistan"
|  |  |  | Дата/Date: | 10.01.2025
BILL OF QUANTITIES
Construction of Pedestrian Bridge connecting Saifullo Abdullo to Barakat Mahalla, Khorog, Tajikistan
No | Description | Unit | Quantity | Unit Price [TJS] | Total Price [TJS]
D | Preliminaries
1 | Mobilization including (Temporary building). The amount is paid after both parties sign the certificate of completion of work | item | 1 |  | 0
2 | Demobilisation | item | 1 |  | 0
3 | Nurse | months | 10 |  | 0
4 | Health and Safety | months | 10 |  | 0
D | Total |  |  |  | 0
All the Figures are rounded up in the total column to two decimal places.
GENERAL NOTES:
* The Bill of Quantities shall be read in conjunction with the Technical Specification and the Tender Design. * Unit price shall include procurement, transportation, professional installing, inspection and all other related expenses, including services State Supervision Service for Architecture and Construction 0.15% * All works must be done professionally and according to this description, specifications, drawings, schemes and details * In case of any difference between BOQ, designs and/or drawings, the instruction of the supervisor Engineer will govern. * The contractor shall provide samples for all materials used in the project before delivery to get approval from the supervisor Engineer. * If the Contractor omits to price any items in the Bill of Quantities, the cost of work for such items will be considered included in the total amount.